Project Report: YCCA Online Tutoring and Support Platform

Kush Gupta, Micheal Bassi, Armaan Chima, Mohamed elalkamy

University of the Fraser Valley

CIS 385: Project Management

Peter Rasquinha

27th November 2025

# ABSTRACT

This report presents a comprehensive project management plan for developing an online tutoring and mentorship platform for the Youth Connect Center Association (YCCA), a non-profit organization supporting Fraser Valley youth. The platform enables virtual academic support, mentor-mentee matching, scheduling, video sessions, and resource sharing to overcome barriers of transportation and scheduling. Drawing from all semester assignments, the document summarizes the project charter, scope, cost, quality, resource, communications, and stakeholder management plans. Detailed artifacts are placed in appendices. Total estimated cost is approximately CAD $2,643 with a 36-day critical path. Analysis confirms the project is fully feasible, low-risk, and strongly aligned with YCCA’s mission. The initiative is deemed completely doable and recommended for immediate implementation.

Table of Contents

ABSTRACT	2

CHAPTER 1: Introduction	5

Project Overview	5

Project Purpose: Youth Support Matching Platform	5

Benefits to the Organization and Community	5

CHAPTER 2: Project Charter	6

Purpose and Authorization	6

Objectives, Scope, and Deliverables	6

Stakeholders and Roles	6

Budget, Timeline, and Success Criteria	6

CHAPTER 3: Scope Management	8

Scope Definition	8

Work Breakdown Structure (WBS)	8

Activity Sequencing and Scheduling	8

Control and Change Management	8

CHAPTER 4: Cost Management	9

Framework Development	9

Needs Assessment	9

Implementation Planning	9

Handbook and Toolkit Design	9

Online Materials Development	9

CHAPTER 5: Quality Management	10

Functionality	10

Features	10

System Outputs	11

Performance	11

Reliability	11

Maintainability	12

CHAPTER 6: Human Resource Management	13

Organizational Chart	13

Responsibility Assignment Matrix (RAM)	13

CHAPTER 7: Communications Management	14

Executive Director/Sponsor	14

Web Development Lead	14

Volunteer Mentor/Tutor Team	14

Youth Users	14

Partner Organizations (Schools, Nonprofits)	14

CHAPTER 8: Stakeholder Management	16

Executive Director	16

Volunteer & Tutor Coordinator	16

Tutors and Mentors	16

School Counsellors	16

Youth Users	16

Web Development Team	16

CHAPTER 9: Conclusion	18

Feasibility Decision	18

Long-Term Value and Sustainability	18

Final Recommendation	18

Conclusion of Report	19

References	20

Appendices	21

APPENDIX A: Project Charter	21

APPENDIX B: STAKEHOLDER MANAGEMENT TABLE	22

APPENDIX C: STAKEHOLDER REGISTER	23

APPENDIX D: SWOT ANALYSIS	24

APPENDIX E: YCCA PLATFORM WORK BREAKDOWN STRUCTURE	28

APPENDIX F: ACTIVITY LIST FOR NETWORK DIAGRAM	28

APPENDIX G: COST ESTIMATE	29

APPENDIX H: QUALITY MANAGEMENT	30

APPENDIX I: ORGANIZATIONAL CHART	31

APPENDIX J: RESPONSIBILITY ASSIGNMENT MATRIX	32

APPENDIX K: STAKEHOLDER COMMUNICATIONS MATRIX	32

APPENDIX L: STAKEHOLDER MANAGEMENT MATRIX	33

# CHAPTER 1: Introduction

## Project Overview

A recognized non-profit organization, the Youth Connect Center Association (YCCA) works to empower young people in Abbotsford and the surrounding Fraser Valley who are between the ages of thirteen and twenty-five. YCCA offers career counselling, academic support, computer literacy training, mentorship programs, and emotional support. Physical capacity, volunteer availability, transportation issues, and scheduling conflicts are some of the organization's challenges. Due to time, location, or budgetary limitations, many young people find it challenging to engage in in-person sessions. YCCA suggested creating a safe, web-based online tutoring and mentorship program to deal with these issues. Using digital tools including scheduling apps, secure messaging, video conferencing, digital resource sharing, and automatic matching systems, this platform will electronically link young people with skilled mentors and instructors. The platform seeks to advance accessibility, inclusivity, and equity while fostering learning, skill development, and long-term mentorship relationships. Appendix A has a condensed Project Charter outlining the platform's goals, schedule, and important stakeholders.

## Project Purpose: Youth Support Matching Platform

All the major assignments from CIS 385 are integrated into one final report, which adheres to PMBOK-aligned project management knowledge areas (Project Management Institute, 2021). One knowledge area scope, schedule, cost, quality, resource, stakeholder, and communications management is narratively summarized in each chapter. Appendices B through L contain all detailed artifacts, including the SWOT Analysis and Stakeholder Register, so the main chapters can continue to be narrative-only as needed. For instance, Appendix B displays the Stakeholder Management Table, and Appendix C contains the Stakeholder Register.

## Benefits to the Organization and Community

The primary objective is to increase tutoring and mentoring accessible through the use of an online environment that removes time and place restrictions. Better donor reporting, more service capacity without additional facility costs, enhanced volunteer coordination, and enhanced youth participation are further advantages. Appendix D's SWOT analysis, which looks at both strengths and threats, demonstrates that this platform is both strategically advantageous and doable for YCCA.

The project is in line with YCCA's objective to empower adolescents by providing equal and easily accessible support services. YCCA can serve more kids, maintain quality, and improve its reach without significantly raising costs by digitizing its services. Appendix E displays the Work Breakdown Structure, which divides the platform into deliverables and shows how each part relates to the organization's objective.

# CHAPTER 2: Project Charter

The project charter outlines the purpose, objectives, scope, and deliverables for the YCCA initiative. It provides authorization to begin the project and identifies the project manager, sponsor, and key stakeholders, along with their roles and responsibilities. The charter also includes the projected timeline, major milestones, budget, and constraints that may affect execution. These details ensure alignment across YCCA and support clear decision-making throughout the project. The full project charter is provided in Appendix A.

## Purpose and Authorization

Mentorship Platform has been approved by leadership within YCCA to extend the organization's reach in providing support to youth within the Fraser Valley and its surrounding remote communities. The project work is to commence on October 1st, 2025, and will be completed by March 1st, 2026. The desired outcome is a secure user-friendly virtual environment where young people from ages 13-25 can access tutoring, mentorship, guidance, and learning resources free from barriers such as commuting, scheduling conflicts, or distance. Mohamed Elalkamy, Project Manager, is hereby granted authority to manage such resources, liaison with all related groups, and oversee the entire development process for and on behalf of the Youth Connect Center Association.

## Objectives, Scope, and Deliverables

The project aims to make a fully functional web-based system for tutoring, mentorship, career guidance, resource sharing, and communication between youth and volunteer mentors. The scope of this project includes the development of the digital platform, onboarding materials for volunteers, the ability of matching youth with mentors, scheduling times, secure messaging, and resource libraries. Key deliverables for this project include the online digital platform itself, training and digital content, integrated tracking features that enable YCCA to carry out its mission of empowering youth through more accessible support and learning opportunities. The project will be conducted based on a hybrid approach-a waterfall for initial planning, agile sprint cycles for ongoing development, testing, and iterative improvement.

## Stakeholders and Roles

The various stakeholders in this project are involved in planning, development, and service delivery. The YCCA Executive Director will provide the strategic direction and approval for the project as the project sponsor. The day-to-day coordination and communication will fall under the responsibility of the Project Manager, Mohamed Elalkamy. The technical development aspect of this project will be led by an external Community Web Developer operating as the Technical Lead. The YCCA Volunteer Network will provide program delivery and volunteer coordination through the Volunteer Mentor Lead. It will also include a School Counsellor Representative to address community and school-based needs and a Youth Representative to make sure that the resource platform is well-suited for youth, covering areas of accessibility, privacy, and usability.

## Budget, Timeline, and Success Criteria

The estimated budget for the development of the platform is $2,643 CAD and that includes training materials, hosting services, content, and outreach events. The timeline of this project is about five months, starting on October 1, 2025, and ending on March 1, 2026. The online services have to be fully operational no later than March 31, 2026. Output will be measured with the following deliverables: a minimum of 60 youth and 15 volunteer mentors signed up during the first two months, a minimum satisfaction rating of 80%, and confirmation of compliance with general youth program privacy standards. Other indicators include increased participation, accessibility, and accounting of youth involved with YCCA across their various programs.

# CHAPTER 3: Scope Management

## Scope Definition

All of the work necessary to develop and deploy the YCCA Online Tutoring and Mentorship Platform is defined by scope management. Tasks including user registration, a mentor-matching system, a scheduling tool, a messaging feature, document sharing, mentor onboarding, and support for youth training are all included in the scope. Setting up physical infrastructure and developing mobile apps are not included. Appendix A contains the whole Project Charter that outlines the high-level scope components.

## Work Breakdown Structure (WBS)

The project is divided into four tiers by the Work Breakdown Structure (WBS). The whole platform development and launch are represented by Level 1. Infrastructure preparation, platform design, content creation, and stakeholder interaction are all included in Level 2. User identification methods, video integration, the development of educational resources, and promotion are all included in Level 3. Tasks including organizing training sessions, gathering feedback, and conducting final testing are included in Level 4. Better task ownership, clarity, cost assessment, and effective time management are all made possible by the WBS. Appendix E contains the full Work Breakdown Structure diagram.

## Activity Sequencing and Scheduling

Activities were connected logically to identify the important path using precedence diagramming and network analysis (Assignment 6). The planning, development, testing, and launch phases of the critical route take 36 working days. Float times were computed using forward and backward passes. Platform design, core development, integration testing, and launch preparation are among the tasks with zero float that make up the critical route. Appendix F has a comprehensive Activity List that details dependencies, task durations, and resource requirements.

## Control and Change Management

A formal change control procedure will be utilized to avoid scope creep. The project manager must examine any suggested modifications, and the sponsor must give their approval. Changes that are approved will be recorded, their effects on time and money will be evaluated, and they will only be put into action if they help achieve the project's goals. This guarantees that the project stays on course and prevents needless delays or overspending. For appropriate stakeholder notice, modifications will be recorded and incorporated to the Stakeholder Communication Matrix (Appendix K) after approval.

A working web platform, mentor training manual, digital resource library, user security system, tools for feedback surveys, and onboarding instructions are important project deliverables. Specific acceptance criteria, such as performance benchmarks, user happiness, dependability, and accessibility, apply to each deliverable. The Responsibility Assignment Matrix (Appendix J), which also specifies who approves each deliverable, contains these criteria.

An organized summary of the project deliverables, schedules, and control systems is provided by the scope management plan. Through the use of WBS, critical path analysis, and change control methods, the project will successfully accomplish its goals and stay in line with expectations.

# CHAPTER 4: Cost Management

## Framework Development

Define Mentorship Goals and Objectives, the first WBS item, focuses on the preparatory work needed to create a formal mentorship framework. This includes evaluating materials with administration, creating a program charter, and holding stakeholder meetings. The estimated expenses are predicated on the average consulting and coordinating fees in Canada, which range from CAD $35 to CAD $45 per hour for professional meetings (Indeed, 2025). It is anticipated that this phase will cost roughly CAD $438 in total.

## Needs Assessment

Creating, disseminating, and evaluating online surveys is part of the second WBS item, Conduct Youth and Community Needs Assessment. Time spent on data analysis and survey development tools are the main causes of this cost. Data analysts normally charge about CAD $35 per hour, whereas survey design tools such as Google Forms or SurveyMonkey cost about CAD $25 to $30 per month (Glassdoor, 2025). This component is expected to cost CAD $435 in total.

## Implementation Planning

Drafting project deadlines, stakeholder evaluations, and final feedback sessions are necessary for the third item, Develop Implementation Plan. Project coordinators and analysts are mostly responsible for this labour-intensive endeavour. The estimated cost is CAD $380 based on an average project management hourly rate of CAD $35–40 (Talent.com, 2025).

## Handbook and Toolkit Design

Digital production, graphic design, and content writing are all included in the fourth component, the Design Mentorship Handbook and Toolkit. Depending on their level of experience, professional writers and designers usually charge between $35 and $50 per hour (PayScale, 2025). Because of the creative and design work intensity, this WBS has the highest total of any item at CAD $650.

## Online Materials Development

Lastly, creating PowerPoint presentations, uploading content, and recording videos are all included in the Develop Online Learning Materials and Visuals section. In Canada, content producers make between CAD $25 and CAD $30 per hour, whereas video editors make between CAD $50 and CAD 65 per hour (Indeed, 2025). Production and digital management activities are included in the projected CAD $440 cost.

# CHAPTER 5: Quality Management

The YCCA Online Support & Tutor Matching Platform Project complies with the necessary requirements for performance, accessibility, dependability, and user satisfaction thanks to the Quality Management Plan. Its goal is to provide young people looking for academic support, career guidance, mentorship, and digital resources with a seamless support experience. For an overview of the quality-related features needed for this project, see Appendix H.

## Functionality

The platform should make it simple for young people to choose the type of support they require (e.g., academic assistance, career guidance, university transition assistance, digital literacy support, etc.).

Based on availability, skill set, language, and urgency, the system must then pair them with a qualified mentor, tutor, or support volunteer.

Users need to be capable of:

- Make an account

- Send in support requests

- Securely communicate with volunteers

- Set up meetings

- Upload the required files, such as resumes and homework assignments.

To help the youth in a timely and efficient manner, volunteers must receive accurate notifications and have access to the information they require.

## Features

Important elements that guarantee an excellent user experience consist of:

- A clever matching algorithm that matches young people with the most suitable mentor or tutor.

- To evaluate academic standing, career aspirations, support requirements, or device requests, use the Youth Intake Questionnaire.

- Youth can track their progress over time by using session logging and progress tracking.

- Multilingual interface to assist diverse communities and young immigrants.

- Tools for Equitable Access, such as a process for requesting desktop computers or assistance with digital literacy.

These characteristics aid in making the platform inclusive, accessible, and suited to the various needs of youth.

## System Outputs

When a support request is submitted, the platform needs to show concise confirmation messages like:

"Your request has been sent in. A mentor will get in touch with you soon. or "A volunteer tutor, Sarah K., has been assigned to you."

Other outputs from the system could be:

- Notification of upcoming sessions

- Updates on progress

- Verifications of device distribution

- Notifications of forthcoming deadlines or meetings

These results increase follow-through rates and keep young people informed and involved.

## Performance

Even during times of high usage, like exam seasons or application deadlines, the platform should continue to be quick, dependable, and responsive.

Among the performance objectives are:

- Quick loading and matching procedures

- Updates on messaging in real time

- Easy scaling to assist young people and new volunteers

- Very little downtime, particularly when demand is high

Future growth should be supported by the system, including the integration of video sessions, the addition of new support categories, and the onboarding of partner organizations.

## Reliability

Maintaining trust with young people, families, and partner organizations depends on system dependability.

Important reliability criteria consist of:

- Consistent uptime for every user

- Precise data processing and safe message transmission

- Protection of young people's personal data and privacy

- Adherence to security regulations pertinent to youth services and nonprofit organisations

A dependable platform guarantees that young people receive the support they require without interruption and lowers administrative overhead.

## Maintainability

Users should experience as little disruption as possible when regular updates are implemented. Among the maintenance tasks are:

- System enhancements and bug fixes

- Updates to the interface to improve accessibility

- Frequent backups of volunteer data, session logs, and user data

- As the volunteer database expands, matching algorithms are updated.

Long-term sustainability and ongoing platform improvement are guaranteed by a solid maintainability plan.

By putting these quality standards into practice, YCCA can provide a reliable, easily accessible digital support system that improves youth outcomes, increases mentorship engagement, and fortifies community ties.

# CHAPTER 6: Human Resource Management

## Organizational Chart

The YCCA Online Support Platform Project's organizational structure and the individuals in charge of each component are depicted in this chart. The project manager oversees overseeing every facet of the development and implementation process, making sure that every team remains in line with the project's goals.

Building the platform, creating the matching algorithm, guaranteeing data security, and preserving system performance are all under the purview of the IT Development Team.

Tutors, mentors, and support volunteers must be recruited, onboarded, screened, and trained by the Volunteer & Training Team. They make sure volunteers are ready to help with career counselling, academic tutoring, and youth mentoring.

By overseeing intake, answering questions, helping with device distribution, and following up to make sure young people get the support they require, the Youth Services Team concentrates on providing direct assistance to youth.

To increase reach and impact, the Marketing & Outreach Team promotes the platform to schools, nonprofits, and youth organizations while managing partnerships, communications, and community involvement.

Every team is essential to maintaining the platform's functionality, usability, and support. Appendix I contains a complete visual organizational chart.

## Responsibility Assignment Matrix (RAM)

Together, these roles form a coordinated structure that keeps the YCCA Online Support Platform running smoothly from both a technical and community-focused perspective. The Responsibility Assignment Matrix (RAM) clarifies who is accountable for each task, reduces overlap, and ensures that every part of the project has a clear owner. By outlining responsibilities up front, the project can move efficiently through development, launch, and long-term operations while maintaining a strong focus on youth support and service quality.

# CHAPTER 7: Communications Management

## Executive Director/Sponsor

High-level updates describing project performance, budget utilization, risks, and strategic alignment are required by the Executive Director. Executives want organized, decision-focused papers that allow for discussion and explanation, therefore a formal Monthly Project Status Report provided in hard copy during a brief meeting is ideal (PMI, 2021). Meetings support governance and approval procedures while encouraging stakeholder participation and accountability (Kerzner, 2022). High-level stakeholders are guaranteed to receive succinct yet useful information in this manner to aid in strategic decision-making (Peter, 2025).

## Web Development Lead

The Web Development Team requires precise technical updates, logs, deadlines, and implementation notes. Because it facilitates cooperation, version control, real-time updates, and task assignment, the Technical Implementation Update via an intranet/project management system is perfect for this stakeholder (Kerzner, 2022). According to PMI (2021), project teams benefit most from common digital platforms that centralize communication, documentation, and responsibility. This guarantees effective tracking and prevents technical stakeholders from miscommunicating (Peter, 2025).

## Volunteer Mentor/Tutor Team

The Volunteer & Tutor Team oversees training logistics, tutor involvement, and scheduling. For this stakeholder, an email-based tutor engagement report is appropriate since it allows for rapid updates, document sharing, and accessible reference without the need for formal meetings (Verma, 2020). For stakeholders that need regular monitoring but don't need to make choices right away, email's push communication feature is perfect (PMI, 2021). It guarantees effectiveness while keeping transparent communication records for coordination (Peter, 2025).

## Youth Users

Students, who are youth participants, interact directly with the digital tutoring platform and want easy-to-access updates. Because it allows for real-time distribution in the setting they are already using, the Platform Usage Summary—which is provided through in-platform notifications—is perfect (Youth Connect Center Association, 2025). Pull-based communication via dashboards or platform alerts is appropriate for customers that need fast, action-based information, according to PMI (2021). For non-technical consumers, this format guarantees low misunderstanding, accessibility, and engagement (Peter, 2025).

## Partner Organizations (Schools, Nonprofits)

As community partners, school counsellors encourage user participation and referrals. Because they need both official documentation for school records and digital access for prompt review or forwarding, the Outreach & Referral Report, distributed via physical copy and email, is acceptable (Youth Connect center Association, 2025). External stakeholders frequently need dual-format communication for both formality and convenience, according to PMI (2021). This strategy improves referral coordination, transparency, and partnership participation (Peter, 2025).

# CHAPTER 8: Stakeholder Management

The YCCA Online Support & Tutor Matching Platform Project requires tailored communication approaches to ensure each stakeholder receives timely, relevant, and purpose-driven information. As stakeholders vary in power, interest, and organizational role, communication methods must support decision-making, operational effectiveness, and youth service quality. The following outlines the communication needs, preferred formats, and stakeholder characteristics for key groups involved in the project.

## Executive Director

High-level updates are essential for the Executive Director, who oversees organizational strategy, governance, and resource approval. A formal monthly project status report, delivered in hard copy during a brief meeting, provides performance insights, budget utilization summaries, risk considerations, and strategic alignment updates. This format supports informed oversight, accountability, and stakeholder engagement.

## Volunteer & Tutor Coordinator

The coordinator requires frequent updates about training logistics, tutor engagement, and scheduling needs. An email-based Tutor Engagement Report is appropriate, as it enables quick updates, document sharing, and an easy reference trail. This push-style communication supports day-to-day monitoring without requiring formal meetings.

## Tutors and Mentors

Tutors and mentors need consistent, clear communication on upcoming sessions, training requirements, onboarding procedures, and platform features. A training and platform update brief delivered via email ensures rapid distribution, attachment of materials, and accessible instructions for operational tasks. Email also provides documentation for future reference.

## School Counsellors

As external community partners, counsellors support youth referrals and engagement. They require updates that can be both formally documented and easily shared. Therefore, an outreach and referral report distributed in both physical copy and email is suitable. This dual approach provides professionalism while maintaining convenience and accessibility for school systems.

## Youth Users

Youth users engage directly with the tutoring platform and require simple, immediate updates relevant to their activities. In-platform notifications through the platform usage summary provide real-time communication that reduces confusion and supports engagement. Pull-based alerts are effective for youth who benefit from fast, actionable prompts within the environment they already use.

## Web Development Team

The development team needs detailed technical information, including logs, deadlines, task updates, and implementation notes. A centralized technical implementation update using a project management or intranet system supports collaboration, version control, and accurate documentation. This method reduces miscommunication and aligns technical workflows.

# CHAPTER 9: Conclusion

## Feasibility Decision

Based on the analyses presented throughout this report, this including scope, cost, schedule, quality, human resources, communication, and stakeholder management. The YCCA Online Tutoring and Mentorship Platform is feasible.

The required budget of $2,643 falls well within the organization’s financial capacity, and the five-month timeline is realistic given the hybrid project methodology. The work breakdown structure and critical path analysis confirm that the necessary tasks can be completed without exceeding resource limitations. Stakeholder assessments show strong organizational support, with technical expertise, volunteer networks, and youth service teams already in place.

Overall, the project is achievable, cost-effective, and strategically aligned with YCCA’s mission to provide accessible youth support across the Fraser Valley.

## Long-Term Value and Sustainability

The platform delivers significant long-term benefits for the organization and the communities it serves. By shifting mentorship and tutoring resources online, YCCA can:

- Expand service capacity without increasing facility or staffing costs

- Provide continuous, barrier-free access for youth in remote or rural areas

- Strengthen volunteer coordination through automated scheduling and secure communication

- Improve reporting, tracking, and outcome measurement for donors and stakeholders

- Reduce administrative effort through digital intake, matching, and progress tracking

From a sustainability point of view, the platform supports scalable growth. As additional volunteers, youth, or partner organizations join, the digital system can adjust with little added cost. The Quality Management Plan ensures ongoing system reliability, security, and maintainability, enabling the platform to evolve alongside community needs. This long-term digital infrastructure positions YCCA to remain relevant and effective in a rapidly changing social and technological environment.

## Final Recommendation

It is recommended that YCCA proceed with full implementation of the Online Support & Tutor Matching Platform. All project evidence indicates that the initiative is low-risk, financially reasonable, operationally manageable, and highly beneficial to the youth population YCCA serves.

To ensure maximum impact, the organization should:

- Maintain strong collaboration between the development team and youth service staff

- Use iterative user testing during the agile sprint cycles to improve accessibility

- Monitor post-launch metrics such as satisfaction ratings, sign-up rates, and engagement trends

- Continue building partnerships with schools and nonprofits to expand reach

If these recommendations are followed, the project will not only meet its initial requirements but will also set the foundation for expanded digital programming in future years.

## Conclusion of Report

The development of the YCCA Online Tutoring and Mentorship Platform represents a strategic and forward-thinking solution to the challenges of accessibility, capacity limits, transportation barriers, and scheduling conflicts faced by youth in the Fraser Valley. Through careful planning across all the following knowledge areas, this final report demonstrates that the project is feasible, sustainable, and aligned with organizational goals.

Once implemented, the platform will enhance youth empowerment, improve educational outcomes, strengthen mentorship relationships, and reinforce YCCA's role as a leader in community-based youth support. This initiative serves not only as a technological upgrade but as a crucial step toward greater equity, inclusion, and long-term community wellness.

# References

Indeed. (2025). Average hourly rates in Canada. https://ca.indeed.com

Kerzner, H. (2022). Project management: A systems approach (13th ed.). Wiley.

Peter. (2025). CIS 385 PowerPoint slides. University of the Fraser Valley.

Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK guide) (7th ed.). Author.

Talent.com. (2025). Project manager salary in Canada. https://ca.talent.com

Upwork. (2025). Freelance designer and video editor rates. https://www.upwork.com

Youth Connect Center Association. (2025). Home. https://yconnect.org/#client

# Appendices

## APPENDIX A: Project Charter

YCCA Online Tutoring and Mentorship Platform

Project Start Date: October 1, 2025 Project End Date: March1, 2026

Budget Information: Estimated budget of CAD $2,643, allocated for platform development, volunteer training and onboarding materials, hosting services, content creation, and community outreach.

Project Manager: Mohamed Elalkamy, Youth Connect Center Association (YCCA) Volunteer Coordinator and Program Support contact@ycca.ca ¦ +1 (604) 555-8742 (official format, fictional contact)

Project Objectives: Develop and launch a secure web-based platform that allows YCCA to deliver free tutoring, mentorship, career guidance, emotional support, and digital resources to youth ages 13–25 across the Fraser Valley and remote regions. Improve service accessibility by reducing barriers such as transportation, scheduling conflicts, and location limitations. Provide a mentor-youth matching system, session scheduling, resource sharing, and communication tools to enhance engagement and program effectiveness. Support YCCA’s mission of “Empowering youth through accessible support, mentorship, and learning opportunities.”

Success Criteria: - Platform fully functional and operational for youth users by March 31, 2026. - At least 60 youth users and 15 volunteer mentors/tutors registered during the first two months. - Minimum 80% satisfaction rating from youth and volunteer surveys after launch. - Secure login, messaging, and data protection meet basic privacy compliance for non-profit youth programs. - Demonstrated improvement in youth engagement, accessibility, and program tracking. .

Approach: Use low-cost web development, leveraging volunteers, WordPress/LMS-embedded systems, and secure cloud hosting solutions. Apply a hybrid PM approach (Waterfall for planning & Agile sprint cycles for development and testing). Conduct bi-weekly review meetings with YCCA leadership, youth representatives, and volunteer mentors. Integrate resource-sharing features (PDF, worksheets, guides) aligned with YCCA’s existing workshops and tutoring programs. Use data tracking to monitor youth participation and support outcomes.

Roles and Responsibilities: Name & Signature; Role; Position; Organization. YCCA Executive Director; Sponsor; Executive Director; YCCA. Mohamed Elalkamy; Project Manager; Volunteer Coordinator; YCCA. Community Web Developer; Technical Lead; Web Developer (Consultant); External Partner. Volunteer Mentor Lead; Team Member; Mentor/Tutor Leader; YCCA Volunteer Network. School Counsellor Representative; Advisor; Community Partner; Abbotsford School District. Youth Representative; User Advisor; Youth Member; YCCA Youth Program.

Comments: · YCCA leadership approved the idea of expanding tutoring to an online format to reach more youth. Partner Schools (SD34 & SD33) appreciated the potential for coordinated referral systems. Youth participants emphasized the need for easy scheduling, privacy, and access to homework help online.

## APPENDIX B: STAKEHOLDER MANAGEMENT TABLE

| Stakeholder Name | Interest Level | Influence Level | Key Concerns / Expectations | Management Strategy |
| --- | --- | --- | --- | --- |
| YCCA Executive Director | High | High | Project alignment with mission, budget control, impact measurement | Manage closely: Monthly status reports, formal approvals, strategic meetings |
| Lead Developer (YCCA IT Team) | High | Medium | Technical feasibility, platform stability, resource availability | Keep informed: Technical meetings, weekly updates, shared project tools |
| Volunteer & Tutor Coordinator | High | Medium | Volunteer recruitment, training, scheduling, process efficiency | Keep informed: Email updates, training reports, engagement feedback |
| Tutors & Mentors | Medium | Medium | Easy-to-use platform, clear scheduling, youth progress tools | Keep satisfied: Platform guides, training workshops, feedback surveys |
| Youth Users (Students) | High | Low | Accessibility, usability, reliability, mentorship support | Keep informed: Notifications, feedback forms, helpdesk support |
| School Counsellors (Partner Schools) | Medium | High | Referral process, student engagement, reporting | Manage closely: Formal referral reports, partnership meetings |
| Donors & Funding Agencies | Medium | High | Impact, scalability, financial transparency | Keep satisfied: Quarterly impact reports, success stories |
| Parents / Guardians | Medium | Low | Safety, privacy, mentorship guidance provided to youth | Keep informed: Email newsletters, policy updates |

## APPENDIX C: STAKEHOLDER REGISTER

| Name | Position / Title | Stakeholder Type | Project Role | Contact Information |
| --- | --- | --- | --- | --- |
| Jane Smith | Executive Director, YCCA | Internal | Project Sponsor | jane.smith@ycca.ca |
| Mohamed Elalkamy | Youth Program Coordinator (YCCA) | Internal | Project Liaison | mohamed.elalkamy@ycca.ca |
| David Chen | Lead Software Developer (Contractor) | External | Technical Advisor | david.chen@devtech.com |
| Sarah Brown | Volunteer & Tutor Coordinator | Internal | Training & Recruitment Lead | sarah.brown@ycca.ca |
| Youth Participants (General) | Students aged 13–25 | External | Platform End Users | Contact via YCCA Portal |

## APPENDIX D: SWOT ANALYSIS

| Strengths | Weakness |
| --- | --- |
| Q. What do we do better than anyone else? A. Providing holistic youth support combining mental health and career development under one roof. Q. How do we stand apart from others? A. Our integrated approach addresses academic, emotional, and professional needs simultaneously. Q. What are our assets, and which are the strongest? A. Skilled mentors, dedicated volunteers, and accessible youth programs, with mentorship being the strongest asset. Q. What unique resources do we have? (Do we have any expertise or unique talents?) A. Expert guidance in education, mental health, and career readiness tailored for youth. Q. What do we offer to others? A. Empowerment, guidance, skill development, and mental wellness support for young people. Q. What do others think we do well? A. Effectively supporting youth through mentorship, workshops, and practical services like tax filing. Q. What is great about our team and our team culture? A. Collaborative, compassionate, and committed to fostering youth growth and | Q. What areas do we need to improve in? A. Offers services primarily for ages 13-25, we could try to reach younger ages. Q. What are we lacking in? A. The Youth Connect Center Association could always use more volunteers. Q.What areas do our competitors have an edge over us? A.We could expand in digital engagement and media presence to reach more people Q. Where are we lacking in resources? A. Some programs may lack participants, which may waste time or resources Q. What are our inefficiencies? A. Some resources are not used fully, and certain programs may overlap with each other Q. Is our mission overly broad? A. It may cover too many areas at once, so we would have to make sure we can handle all programs at once Q. What controllable factors are being neglected? A. We don’t use social media enough and don’t always collect feedback from members Q. What factors make us lose members? A. Activities or programs that are poorly organized can reduce engagement |

| community impact. Q. Do we have a sustainable competitive advantage? A. Yes, our comprehensive, multi-service model for youth empowerment is rare and hard to replicate. |  |
| --- | --- |
| Opportunities | Threats |

| Q. What external changes in our community, school or beyond present interesting opportunities? A. Growing demand for online tutoring and virtual mentoring Q. Is there another organization providing a complimentary service that we can partner with? A. Partnerships with schools, NGOs, and community groups Q. Is there an unmet need in our community that we can uniquely fill? A. Unmet need for affordable youth tutoring in the Fraser Valley Q. Is there an underserved population in our community that could benefit from what we do? A. Underserved youth in rural areas can benefit Q. What facilities, resources or personnel could we acquire (or relinquish) to improve our position? A. Access to grants, new volunteers, and better digital infrastructure Q. How can we take advantage of technology? A. Use online platforms, AI-based tools, and mobile apps to expand reach Q. What economic, environmental, political or societal shifts or trends could benefit us? A. Rising focus on youth mental health and digital education support Q. How can we use the press/media to our advantage? A. Media coverage of youth empowerment could help raise visibility | Q. Who or what (outside of our group) can endanger our project? A. Other competing non-profit organizations that have the same idea Q. What obstacles stand in the way of our goals? A. Organization scalability, legal issues, and coordination with schools or institutions Q. Is there an organization that already does this work that we’d be duplicating or competing with? A. Yes, other nonprofits, school programs, and community centres all compete with our organization Q. Do we have to rely on others for critical steps in our process that could possibly derail our project or timeline? A. Yes, the organization is a non-profit, and as a result, it heavily relies on donations from others. No donations means the organization's objective and purpose are pointless. Q. What economic, environmental, political or societal shifts or trends could endanger our competitive edge? A. Increasing mental health and financial instability could cause issues in the long run and potentially overload the services YCCA offers. Q. Do we risk negative press or community backlash? A. Incidents regarding youth or how money is dispersed/managed could 8 |
| --- | --- |

|  | cause negative backlash within the community. |
| --- | --- |

## APPENDIX E: YCCA PLATFORM WORK BREAKDOWN STRUCTURE

| WBS Code | Task Name / Description |
| --- | --- |
| 1.0 | Launch YCCA Youth Mentorship Program |
| 1.1 | Program Planning & Research |
| 1.1.1 | Define mentorship goals and objectives |
| 1.1.2 | Conduct youth and community needs assessments |
| 1.1.3 | Research existing mentorship frameworks |
| 1.1.4 | Develop a detailed implementation plan |
| 1.2 | Onboard Learning & Development |
| 1.2.1 | Create mentor and mentee orientation materials |
| 1.2.2 | Organize onboarding and interactive sessions |
| 1.2.3 | Develop guidelines for quality and performance standards |
| 1.2.4 | Conduct feedback and readiness assessments before launch |
| 1.3 | Create Learning Content |
| 1.3.1 | Design mentorship handbook and resource toolkit |
| 1.3.2 | Develop online learning materials and visual content |
| 1.3.3 | Review and edit materials for accuracy and clarity |
| 1.3.4 | Validate final content for implementation and training use |

Note. This WBS outlines the hierarchical structure for the Youth Connect Centre Association (YCCA) Youth Mentorship Program, showing project levels from initiation to content creation.

## APPENDIX F: ACTIVITY LIST FOR NETWORK DIAGRAM

| Activity | Title | Immediate Predecessor | Activity Time |
| --- | --- | --- | --- |
| A | Define mentorship goals & objectives |  | 3 |
| B | Conduct youth & community needs assessment |  | 7 |
| C | Research existing mentorship frameworks |  | 5 |
| D | Develop detailed implementation plan | A, B, C | 6 |
| E | Create mentor & mentee orientation materials | D | 5 |
| F | Organize onboarding & interactive sessions | E | 4 |
| G | Design mentorship handbook & resource toolkit | D | 8 |
| H | Develop online learning materials & visuals | G | 10 |
| I | Review & edit learning materials | G, H | 3 |
| J | Validate final content & readiness assessment | F, I | 2 |

## APPENDIX G: COST ESTIMATE

| WBS Items | # Units / Hrs | Cost / Unit (CAD) | Subtotals (CAD) | WBS Level 2 Totals (CAD) | % of Total |
| --- | --- | --- | --- | --- | --- |
| 1. Define Mentorship Goals & Objectives |  |  |  | 438 | 18.7% |
| Stakeholder meetings | 3 hrs | 40 | 120 |  |  |
| Develop program charter & success criteria | 6 hrs | 38 | 228 |  |  |
| Review with administration | 2 hrs | 45 | 90 |  |  |
| 2. Conduct Youth & Community Needs Assessment |  |  |  | 435 | 18.6% |
| Design online survey | 1 unit | 30 | 30 |  |  |
| Distribute survey to students | 5 hrs | 25 | 125 |  |  |
| Analyze survey data & summarize findings | 8 hrs | 35 | 280 |  |  |
| 3. Develop Implementation Plan |  |  |  | 380 | 16.2% |
| Draft plan outline & timeline | 6 hrs | 35 | 210 |  |  |
| Review & finalize with stakeholders | 3 hrs | 30 | 90 |  |  |
| Obtain feedback & approval | 2 hrs | 40 | 80 |  |  |
| 4. Design Mentorship Handbook & Toolkit |  |  |  | 650 | 27.7% |
| Write handbook content | 10 hrs | 35 | 350 |  |  |
| Graphic design for handbook | 5 hrs | 50 | 250 |  |  |
| Print or export digital handbook | 1 unit | 50 | 50 |  |  |
| 5. Develop Online Learning Materials & Visuals |  |  |  | 440 | 18.8% |
| Record & edit video modules | 4 hrs | 60 | 240 |  |  |
| Create PowerPoint slides for sessions | 5 hrs | 30 | 150 |  |  |
| Upload materials to online portal | 2 hrs | 25 | 50 |  |  |
| TOTAL PROJECT COST ESTIMATE |  |  |  | 2,343 CAD | 100% |

## APPENDIX H: QUALITY MANAGEMENT

| Aspect | Items |
| --- | --- |
| Functionality | Support Request Submission |
|  | Tutor / Mentor Matching |
|  | Session Scheduling |
|  | Youth Intake & Assessment |
| Features | Progress Tracking |
|  | Multi-Language Support |
|  | Volunteer Profiles |
|  | Device Request Workflow (for desktops) |
| Performance | Scalability |
|  | Fast Matching Algorithm |
|  | Real-Time Notifications |
|  | High Uptime During Peak Periods |
| Maintainability | Regular Software Updates |
|  | Automated Data Backups |
|  | Easy Module Expansion (new support categories) |
| Reliability | Consistent Match Accuracy |
|  | Secure Youth Data Protection |
|  | Stable Communication Tools (chat + scheduling) |
|  | Improved Access for Low-Income Youth |

## APPENDIX I: ORGANIZATIONAL CHART

## APPENDIX J: RESPONSIBILITY ASSIGNMENT MATRIX

This table links the WBS activities to organizational departments, indicating roles as Responsible (R), Performs (P), or jointly Responsible & Performs (RP).

| Departments (OBS) | 1.1.1 Create Wireframes | 1.1.2 Design UI Mock-ups | 2.1.1 Develop Backend API | 2.1.2 Implement Frontend Interface | 3.1.1 Conduct Beta Testing | 3.1.2 Launch Promotional Campaign |
| --- | --- | --- | --- | --- | --- | --- |
| Design & User Experience Dept. | R | R | P | P |  |  |
| Software Development Dept. | P | P | R | R |  |  |
| Communications & Outreach Dept. |  |  |  |  | R | R |
| Finance & Operations Dept. |  |  |  |  | RP | RP |

## APPENDIX K: STAKEHOLDER COMMUNICATIONS MATRIX

| Stakeholders | Document Name | Document Format/Mode | Contact Person / Position | Due |
| --- | --- | --- | --- | --- |
| YCCA Executive Director | Monthly Project Status Report | Hard copy and meeting | Executive Director | First of month |
| YCCA Volunteer & Tutor Coordinator | Tutor Engagement Report | Email | Volunteer & Tutor Coordinator | Bi-weekly |
| Tutors/Mentors | Training & Platform Update Brief | Email | Lead Tutor/Mentor | First Monday of each month |
| Youth Users (Students) | Platform Usage Summary | In-platform notification | Student User Representative | Monthly |
| YCCA Web Development Team | Technical Implementation Update | Intranet / project management system | Lead Developer | Weekly (Friday) |
| School Counsellors | Outreach & Referral Report | Hard copy and email | School Counsellor | Quarterly |

## APPENDIX L: STAKEHOLDER MANAGEMENT MATRIX